EE/CprE/SE 491 WEEKLY REPORT 2

09/22 – 09/28

Group number: 06

Project title: AI Arcade

Client: Josh Clausman/SilverTree Studios

Faculty Advisor: Julie Rursch

Team Members/Role:

Alex Stoner - Software

Colten Stevens – Software

Drew Swanson - Software

Dylan Kramer - Hardware

Gavin Thennes - Software

Michael Berg - Hardware

- Weekly Summary

This week, the group accomplished a few different things. First off, we met with our faculty advisor, which helped us get more information on senior design, and just general advice overall. Secondly, we got the rest of our parts ordered (and delivered), so we can get a functional prototype built. One group member 3D printed a mini arcade machine that will hold our parts, so we can have a functional machine (hopefully) to allow people that fit our defined user group to test it. Some group members did research into what our usability study could look like, and some questions that we would be looking to answer through it.  Our goal in the next few weeks is to physically built the AI arcade machine, get the software playable on it, and start figuring out what needs to be improved. This will be determined through TONS of testing. This week, a few group members also messed with the codebase and tried to get an outside AI model connected to it. This is an important piece of the software, and something we need working when the actual machine is functional.

- Past week accomplishments

- Drew Swanson: This past week I worked on a first template of a usability report we can use when getting subjects to test our system. It includes all necessary aspects we need to know to properly conduct a survey and test our system. I also worked with Colten to get the Opencode AI model connected to the local emulator. We figured out how to get OAuth to work and got GPT Terra connected to his laptop. We got the AI prompt window to open, just as the screenshot Josh sent us showed. Some errors appeared, and we worked hard on mitigating them.

- Colten Stevens: This past week I worked on getting opencode to run alongside our code base to allow an AI agent to make live changes to the premade retro games. In order to execute this it involved downloading WSL cloning the codebase into a directory in a Linux distro and installing several packages in the distro such as cargo, rustup etc. Me an Drew figured out how to get OAuth to work and got GPT Terra connected to my laptop and got the authoring window open. This process involved a lot of code debugging and a couple of wrong turns as our initial implementation was attempted on a windows OS. We believe that all the errors are fixed to allow authoring the AI agents, but we need to have a stronger model attempt to work on the code live.

- Michael Berg: This past week I to 3D printed all the pieces for our prototype arcade machine. I did research into possible different STL files to use and I found a free one that works with our core hardware (raspberry Pi). Each print took anywhere between 10-12 hours due to the size of the pieces.  I also did research into components needed to get the machine running (things like a screen, buttons, and a joystick). Beyond that I got the software running on my own machine but have not gotten it connected to the AI to start doing code modifications and begin safeguarding the system.

- Dylan Kramer: This past week I started messing with the codebase and trying to get my ChatGPT connected to the AI Arcade software. Next, I got the rest of the parts ordered. On top of that, I got a meeting scheduled and facilitated with our faculty advisor. We met with her and got a bunch of input and advice on senior design as a whole. I took notes during the meeting and provided them to my team. I also started thinking about what we need to start researching/user testing once our prototype is ready to go. Once the prototype is ready (we are starting that this week), we want to start getting users within our defined user group to play with it. I want to see how different prompts react and take notes on it, so we can determine what needs to be improved. Lastly, I booked our meeting room for our meeting with our client.

- Alex Stoner: This past week I started to do research into how we will structure our user testing. A big component of the project will be understanding the user's needs, so I started to write down my thoughts. I went back to my usability study from Technical Communications as a guide for how we can approach this study and started to think through the types of questions that we hope to answer. I found that the questions and tasks we will have the users complete will fall mainly into two different categories: “what do the users want to do” (experiences, features, etc.) and “how do the users go about doing it”. I created a list of questions that I thought we could ask and started to think through possible tasks. Through the work that I completed, I hope it will be the basis of user testing that we can over the next few weeks to better understand our project’s scope. I did this individually and I spent completed it over the weekend.

- Gavin Thennes: This past week i have gotten the codebase connected to opencode and had some problems setting up. However, after reading discussions with our client and colten about troubleshooting steps, i realized that i had the same problem with WSL not being installed on my machine and was having problems with the project on windows. I ended up creating a virtual ubuntu machine for this project and have gotten the project working with ai features through opencode on ubuntu. This is a better implementation as our project will be deployed to a PI running linux, which will allow me to develop on a much closer environment to the final product.

- Individual contributions

| NAME | Individual Contributions | Hours this week | HOURS cumulative |
| --- | --- | --- | --- |
| Drew Swanson | - Produced usability report template - Brainstormed user feedback questions - Studied codebase used for AI - Worked on connecting opencode to emulator | 6 | 9 |
| Colten Stevens | - Set up OpenCode and WSL - Configured AI integration - Debugged the implementation of live AI edditing | 6 | 9 |
| Michael Berg | - 3d printed pieces of prototype - Researched additional components - Started to look at using the software on own computer | 6 | 9 |
| Dylan Kramer | - Scheduled and facilitated meeting W/ Faculty advisor - Took meeting notes - Got rest of the parts ordered - Brainstormed user feedback/research questions | 3 | 6 |
| Alex Stoner | - Started to design usability study - Looked into the codebase and connecting an AI model to it | 3 | 6 |
| Gavin Thennes | - Set up opencode - Created development VM - Started deeper studying of codebase | 3 | 6 |

- Plans for the upcoming week

- Colten Stevens: My plans for next week are to meet with a group to build the arcade cabinet, get the code base AI implementation running on my teammates computers and talk to our advisor about getting Claude or chat gpt pro subscriptions through Iowa state.

- Drew Swanson: Get 3d printed arcade assembled. Connect AI to emulator to fully test system availability. Work on usability report structure and questions.

- Michael Berg: Get the 3d printed arcade machine assembled and attempt to connect the software to the AI to get code modifications working.

- Dylan Kramer: My goal is to start working on our SD Website and design document. I also plan to start working/thinking through the best ways to test the prototype once it’s complete, and get good feedback. Alex and I will meet to start talking about this.

- Alex Stoner: I am going continue to develop the usability study and start to test the program myself. I am going to start identifying areas that need to be fixed and updated to ensure proper functionality for the study.

- Gavin Thennes: My goal is to work with the team to get the usability study out and get feedback from others. I also am going to look into ways of securing the chat sessions both locally and what possibilities are available externally.